## Sheet1
risico analyse | Gevolg | Kans | impact | Score
Data lost: | Delay | 1 | 3 | 3
Unclear project boundries: | Delay | 1 | 3 | 3
No coorperation from the client: | Delay | 2 | 3 | 6
Employees that wont be able to work: | Delay | 2 | 2 | 4
Internet provider error: | Delay | 2 | 3 | 6
Ddos: | Delay | 1 | 3 | 3
If a task gets delayed other tasks get delayed: | Delay | 2 | 2 | 4
Conflicts between team members: | Delay | 2 | 4 | 8
Aditional requirements are added: | Delay | 1 | 4 | 4